## Upgrade-Steps
Upgrade Steps
Step No | Start_time (IST) | Owner | Step Name | Description | Status
1 | 2021-03-23 | Ajay (DBA) | Copy SQL 2019 Slipstream setup on SQLREPL1 & SQLREPLDR |  | Done
2 | 2021-03-23 | Ajay (DBA) | Mute radar alert for desco & deshaw pods |  | Done
3 | 2021-03-23 | Ajay (DBA) | Raise Arc Status notification |  | Done
4 | 2021-03-23 | Ajay (DBA) | Raise Systems Status notification |  | Follow up
5 | 2021-03-23 | Ajay (DBA) | Raise Sys request for VM Snapshot/Restore for Prod |  | Done
6 | 2021-03-23 | Ajay (DBA) | Raise request for required space on servers |  | Done
7 | 2021-03-25 | SRE | Create slack channel for coordinating with Desco System, VM Admin & DBRE |  | Follow up
8 | 2021-03-27 08:45 | Ajay (DBA) | Validate Replication Health with Tracer Tokens
9 | 2021-03-27 09:00 | Ajay (DBA) | Offline SQL Server Database Services for SQLPROD SqlClusters
10 | 2021-03-27 09:10 | Ajay (DBA) | Set Start Mode to 'Disable' for SqlInstances on SQLPROD SqlClusters
11 | 2021-03-27 09:20 | SRE | Shutdown SQLREPL1 & SQLREPLDR hosts
12 | 2021-03-27 09:20 | SRE | Desco SRE to take VM & Disk Snapshot for distributor nodes
13 | 2021-03-27 09:20 | SRE | Start SQLREPL1 & SQLREPLDR hosts
14 | 2021-03-27 09:45 | Ajay (DBA) | RDP SQLREPLDR, and Upgrade Sql to 2019. Reboot.
15 | 2021-03-27 10:05 | Ajay (DBA) | Validate upgrade by querying replication metadata & @@version
16 | 2021-03-27 10:05 | Ajay (DBA) | Connect SQLREPLDR from SSMS, and failover AG with SQLREPLDR as Primary
17 | 2021-03-27 10:10 | Ajay (DBA) | RDP SQLREPL1, and Upgrade Sql to 2019. Reboot.
18 | 2021-03-27 10:30 | Ajay (DBA) | Validate upgrade by querying replication metadata & @@version
19 | 2021-03-27 10:30 | Ajay (DBA) | Resume data movement on AG for [distribution] database on SQLREPL1
20 | 2021-03-27 10:30 | Ajay (DBA) | Connect SQLREPL1 from SSMS, and failover AG with SQLREPL1 as Primary
21 | 2021-03-27 10:30 | Ajay (DBA) | Review health using AG native dashboard
22 | 2021-03-27 10:30 | Ajay (DBA) | Review SQL Server ERRORLOG
23 | 2021-03-27 11:00 | Ajay (DBA) | Set Start Mode to 'Manual' for SqlInstances on SQLPROD SqlClusters
24 | 2021-03-27 11:05 | Ajay (DBA) | Bring online SQL Database Services for SQLPROD SqlClusters
25 | 2021-03-27 11:15 | Ajay (DBA) | Review health using Replication Monitor
26 | 2021-03-27 11:25 | Ajay (DBA) | Review SQL Server ERRORLOG on SQLPROD SqlClusters